## RMS
Screen/Function | Description | Level | LOC | Planned-In | In Charge | Done-In | RDS | Status | Updated | Update Details | Total loc
Home Page | As a guest user (not logged in), I want to access the homepage of the website, So that I can view the main content and features of the platform, including: - Navigation Bar to explore main sections like Movie, Theater, Category, and Contact - Banner Slider to see current promotions or highlights - Hot Movie in Month to discover popular movies with key details - Events Section to stay informed about upcoming or ongoing events - Footer to find quick links, support information, and mobile app access | Level 3 | 120 |  | Hieu |  |  | Done
User Login | As a user with a specific role, I want to log in using my email and password so that I can easily remember my account. | Level 1 | 60 |  | Hieu |  |  | Done
Search movie by name | As a guest or registered user, I want to search for a movie by its name so that I can quickly find the movie I want to watch. | Level 1 | 60 |  | Hieu |  |  | Done
Movie showing | As a user, I want to see movies filtered by category so that I can easily choose. | Level 1 | 60 |  | Hieu |  |  | Done
Movie detail | As a user, I want to see the details of a movie so that I can easily choose. | Level 2 | 90 |  | Hieu |  |  | Done
Schedule movie | As a user, I want to see the detailed schedule of a movie so that I can easily make a choice. | Level 1 | 60 |  | Hieu |  |  | Done
Booking movie and payment | As a user, I want to see which seats for that movie are mine and which are others so that I can easily choose. | Level 1 | 60 |  | Hieu |  |  | Done
Blog Details | .. | Level 1 | 60 | Iteration 2 | AnhPT | Iteration 2 |  | To Do | Not Yet
Posts List | .. | Level 1 | 60 | Iteration 2 | HaTH | Iteration 2 |  | To Do | Not Yet
Post Details | .. | Level 1 | 60 | Iteration 2 | KienNT | Iteration 3 |  | To Do | Not Yet
Setting List | .. | Level 1 | 60 | Iteration 3 | TuanNV | Iteration 3 |  | To Do | Not Yet
Setting Details | .. | Level 1 | 60 | Iteration 3 | ThuyTT | Iteration 3 |  | To Do | Not Yet
Users List | .. | Level 1 | 60 | Iteration 3 | TuanNV | Iteration 3 |  | To Do | Not Yet
User Details | .. | Level 1 | 60 | Iteration 3 | ThuyTT | Iteration 3 |  | To Do | Not Yet
Note on C1: KienNT: Complexity Levels Level 1: 3-5 fields OR 2 trans Level 2: 6-7 fields OR 3 trans Level 3: 8-9 fields OR 4 trans Level 4: 10-11 fields OR 5 trans Level 5: 12-13 fields OR 6 trans Level 6: 14-15 fields OR 7 trans Level 7: >15 fields OR >7 trans
Note on E1: kiennt: Kế hoạch sẽ làm trong iteration nào?
Note on G1: kiennt: Thực tế đã làm xong trong iteration nào?
Note on H1: KienNT: Phân tích yêu cầu và thiết kế cho màn hình/chức năng được mô tả trong phần nào của tài liệu RDS?
Note on J1: kiennt: Chức năng đã được update/bổ sung trong iteration nào sau khi được review
Note on K1: kiennt: Các nội dung update cụ thể, mô tả theo định dạng sau: dd/MMM-AccountName: Abc Xyz - dd/MMM: ngày thực hiện update (ví dụ 13/Oct) - AccountName: tài khoản của SV đã thực hiện update (ví dụ KienNT hoặc KienNTHe171209) - Abc Xyz: mô tả nội dung update
Note on C2: KienNT: Level 1: 3-5 fields OR 2 trans Level 2: 6-7 fields OR 3 trans Level 3: 8-9 fields OR 4 trans Level 4: 10-11 fields OR 5 trans Level 5: 12-13 fields OR 6 trans Level 6: 14-15 fields OR 7 trans Level 7: >15 fields OR >7 trans

## Params
Screen/Function Complexity Levels
Screen complexity can be defined based on the screen's fields OR screen/function's transactions | Level | Fields | Trans* | LOC | Notes
- Transactions can be counted as number of transactions to the database or external systems/subsystems | Level 1 | 3-5 | 2 | 60 | 3-5 fields OR 2 trans
- Fields are screen's actionable components or database table fields; if there are some transactions those are | Level 2 | 6-7 | 3 | 90 | 6-7 fields OR 3 trans
not "related" to any fields, each of those transactions are counted as two fields and add those extra number | Level 3 | 8-9 | 4 | 120 | 8-9 fields OR 4 trans
to the total number of fields to define the screen/function complexity | Level 4 | 10-11 | 5 | 150 | 10-11 fields OR 5 trans
| Level 5 | 12-13 | 6 | 180 | 12-13 fields OR 6 trans
Some samples of screen complexity defining are as following | Level 6 | 14-15 | 7 | 210 | 14-15 fields OR 7 trans
Sample #1 | Level 7 | >15 | >7 | 240 | >15 fields OR >7 trans
*One trans (transactions) = Two fields (actionable screen components)
Sample #2
Sample #3